## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
a | Open account | As a bank administrator, I want to enter user's birthday, name, address, and the initial deposit amount, so that I could create an account for the user. | 1 | 1 | 1.Make sure than the user provides name, address, birthday, the account type. 2. For current account, initial overdraft limit needed to be set. 3. For saver account, notice period needs to be set. 4. For junior account, the user must be less than 16 years old. |  | 4.01 | 4.07
a1 | Add new customer | As a bank administrator, I want to obtain a customer's name, birthday, address, and credit number, so that I can check whether the user meets the requirement of particular account or not. | 1 | 1 | 1. Make sure the input format is correct.(e.g. birthday should be 8-digit). 2. Make sure the user doesn't exist in the database. 3. For current account, initial overdraft limit needed to be set. 4. For saver account, notice period needs to be set. 5. For junior account, the user must be less than 16 years old. |  | 4.01 | 4.07
a2 | Credit check | As a bank manager, I want to check whether the user has bad credit befor creating an account, so that I won't open account for people who are distrusted. | 4 | 4 | 1.Make sure the user is not in the bad-record list. | A file that contains the name of people who have bad credit is stored and updated. | 4.22 | 4.28
a3 | Create account | As a bank administrator, I want to create the account for the customer, and provides a PIN and account numer, so that they can use it to transact. | 1 | 1 | 1. Make sure the PIN could be auto-generated, and is random 6-digit number, 2. while account number is 5-digit unique number. 3. Make sure the account type is recorded. 4. For the saver account, make sure the create time is recorded. |  | 4.01 | 4.07
b | Withdraw funds | As a cutomer, I want to input my account number, PIN, and withdraw amount, so that I can withdraw funds . | 2 | 2 | 1.Make sure the input account number and PIN is matched. 2. Make sure the user is in the database. 3.Make sure the user has enough money. 4. Make sure the account is not suspended. |  | 4.8 | 4.14
b1 | Saver account withdraw | As a cutomer with save account, I could only withdraw money after particular notice period, so that I will control my money flow and save my money. | 3 | 2 | 1.Make sure the notice period has been set when the user create a saver account. 2.Make sure the user could only withdraw money after that notice period. |  | 4.8 | 4.14
b2 | Junior account withdraw | As a customer with junior account, I want to withdraw money from a junior account. | 3 | 2 | 1.Make sure the withdraw amount doesn't exceeds user's balance |  | 4.8 | 4.14
b3 | Current account withdraw | As a customer with current account, I want to withdraw additional funds, so that I can have better flexibility | 3 | 2 | 1. Make sure an overdraft limit is initialized when a current account is created. 2.Make sure the withdraw amount doesn't exceed the overdraft limit. |  | 4.8 | 4.14
c | Deposit funds | As a depositor, I want to input the account number and deposit amount, so that Ican deposit money. | 3 | 3 | 1.Make sure the account number that the user input does exist in the database. 2.Make sure the account is not suspended. |  | 4.15 | 4.21
c1 | Deposit cash | As a depositor , I want to input account number and deposit cash amount, so that I can deposit money to that account . | 3 | 3 | 1.Make sure that the deposit will be added to the balance immediately. |  | 4.15 | 4.21
c2 | Deposit check | As a depositor , I want to input account number and deposit with check, so that I can deposit money to that account later. | 3 | 3 | 1.Make sure that deposit amount is recorded as uncleared funds, and doesn't add to the balance immediately. 2. Notify the user when the amount will be issued. |  | 4.15 | 4.21
c3 | Clear funds | As a bank employee, I want to periodically clear uncleared funds, so that I could issue the deposit as check . | 4 | 4 | 1. Make sure the uncleared funds would be issued to the balance after the clearing process finished. 2. Make sure the uncleared funds would be set to 0 afterwards. 3. Make sure to notify the user that the funds has been issued. 4. Make sure the clearing system could be automatic and periodic. |  | 4.22 | 4.28
d1 | Suspend account | As a bank administrator, I want to input the account number and suspend that account, so that no further transaction would be allowed. | 2 | 2 | 1.Make sure the user is in the database. 2. Make sure the user could not deposit, withdraw, but could close account. 3. Make sure the user's status could be activated through the same process. |  | 4.8 | 4.14
d2 | Activate account | As a bank administrator, I want to input the account number and activate that account, so that transaction could be continued. | 2 | 2 | 1.Make sure the user is in the database. 2.Make sure the user's status could be activated through the same process. |  | 4.8 | 4.14
e | Close account | As a bank administrator, I want to input the account number, so that I can close the account. | 3 | 4 | 1.Make sure the user's balance is 0 before they leave. Otherwise, they will have to deposit or withdraw to make it 0. 2. Make sure to notify the user how much money should be further withdraw or deposit. |  | 4.22 | 4.28